# Project Run Manual — Orthopedic 510(k) Predicate-Graph Study

## A complete, self-contained how-to for running the study by hand — JupyterLab, GitHub, OSF

This manual is written so that **you and your partner can run the entire study on your own computers,

start to finish, without Claude Science.** Everything is plain Python in JupyterLab plus a web browser

for GitHub and OSF. Where a step is tedious to do by hand, we note that Claude Code (the terminal

coding assistant) can run it for you — but nothing here requires it.

Two people, two roles. The study is designed around a split:

Analyst (one of you) builds the study: registers the plan, freezes the data, runs the pipeline.

Verifier (the other) independently reproduces every number and signs off.

You can swap who plays which role, but the verifier must not be the person who ran the analysis.

The golden rule of order — do not break it:

Register the plan on OSF *first*. Freeze the data *second*. Run the analysis *third*.

This is what makes the study honest: the plan is timestamped before the results exist, so nobody can

say the findings were shaped to fit. If you freeze or analyze before registering, that protection is

gone.

# 0. What you need before you start (~20 min, once)

## 0.1 Software (both people, on each computer)

Install, in order:

Python 3.11+ — from python.org or via Anaconda/Miniconda.

JupyterLab and the analysis libraries. Open a terminal and run:

pip install pandas networkx pymupdf numpy scipy jupyterlab jupytext

Git — from git-scm.com (Mac: xcode-select --install also gives you git).

(Optional) Claude Code — from the Anthropic docs. Only needed if you want it to run the long

or fiddly steps for you; every step also has manual instructions.

Confirm they work:

python --version        # 3.11 or higher
jupyter lab --version   # prints a version
git --version           # prints a version

## 0.2 Accounts (free)

OSF — https://osf.io → Sign Up (use an institutional email if you have one).

GitHub — https://github.com → Sign Up.

## 0.3 Get the project files

All the code and documents live in this project's artifact bundle. Download and unzip it into a working

folder, e.g. ~/predicate-study/. You should end up with:

predicate-study/
├── PREREGISTRATION.md / .docx          # the locked analysis plan
├── PROJECT_RUN_MANUAL.md / .docx       # this document
├── RUN_MANUAL.md / .docx               # the earlier 2-role manual (reference)
├── requirements.txt
├── notebooks/
│   ├── 00_freeze_snapshot.ipynb
│   ├── 01_corpus.ipynb
│   ├── 02_download_pdfs.ipynb
│   ├── 03_extract_edges.ipynb
│   ├── 04_recalls.ipynb
│   ├── 05_classify.ipynb
│   ├── 06_graph_and_analysis.ipynb
│   ├── 07_maude.ipynb
│   └── 08_verify.ipynb
└── (data/ and snapshot/ are created when you run the notebooks)

Claude Code shortcut: you can hand Claude Code this manual and say "set up the folder as described

in §0.3," and it will create the structure and check your installs. Optional.

# 1. PART ONE — Register the plan on OSF (Analyst; ~30 min) — DO THIS FIRST

Nothing is frozen or analyzed until this is done.

## 1.1 Read and finalize the plan

Open `PREREGISTRATION.docx`. Read it end to end — it is the study's contract.

Fill the two placeholders: Authors and Contact.

Re-read §4 (Hypotheses) and §7 (Confirmation criteria) carefully. Once registered these are

locked. Make sure H1–H5 and every threshold (e.g. "≥ 50 post-recall citations") say what you intend.

Confirm §3 (prior-knowledge declaration) still reads truthfully — it discloses the earlier 9-code

pilot and the exploratory freeze. Do not delete these disclosures. They are what make the

registration credible.

## 1.2 Create the OSF project

Sign in at osf.io → ＋ Create new project.

Title: Orthopedic 510(k) Predicate-Graph Study

Description:

> A retrospective, observational network analysis of predicate-device citations among U.S. FDA

> 510(k)-cleared orthopedic implants, examining how recalled devices persist as predicates for later

> clearances. Descriptive; no intervention; no manufacturer naming.

License: CC-BY 4.0. Click Create.

## 1.3 Create the preregistration

In the project → left menu Registrations → New registration.

Template: choose "OSF Preregistration" (or "Preregistration Template for Existing Data" if

offered — either works here). If neither is clear, choose "Open-Ended Registration" and paste the

entire PREREGISTRATION.md into the single narrative box.

Fill each form field by copying the matching section from PREREGISTRATION.docx:

| OSF form field | Copy from |
| --- | --- |
| Title | top of the document |
| Prior work / has data been collected | §3 (paste in full — pilot + exploratory freeze) |
| Hypotheses | §4 |
| Design / variables / definitions | §5 |
| Analysis plan | §6 |
| Outcomes / confirmation criteria | §7 |
| Statistical tests + sensitivity | §8 |
| Exploratory / other | §9 |
| Limitations | §10 |

## 1.4 Submit and save the timestamp

Click Register. Choose "Register without an embargo" (public now) or "with an embargo"

(sealed, auto-public later — pick this if you want the plan private until you publish).

OSF creates a frozen, timestamped, read-only registration with its own URL.

Copy that URL and paste it into a new file `RUN_LOG.md` in your project folder. It is your proof

of pre-registration and goes in the manuscript.

⛔ Checkpoint: do not proceed to Part Two until you have the registration URL.

# 2. PART TWO — Freeze the data snapshot (Analyst; ~15 min) — AFTER registration only

## 2.1 Launch JupyterLab

In a terminal, from your project folder:

cd ~/predicate-study
jupyter lab

Your browser opens JupyterLab. Navigate into notebooks/.

## 2.2 Run Stage 0

Open `00_freeze_snapshot.ipynb`.

Run → Run All Cells.

It contacts openFDA once, downloads every 510(k), recall, and enforcement record for the 154

orthopedic product codes, and writes them to a new snapshot/ folder plus SNAPSHOT.json.

Read the final CHECKPOINT line: it prints the freeze date (today or later — after your

registration), the code count (154), device count (~15,600), summary count (~13,300), and recall

count (~6,300). These will differ slightly from the numbers in the prereg's §3.3 — that is

expected FDA database growth, and the prereg already says so.

## 2.3 Attach the snapshot to OSF

Upload snapshot/SNAPSHOT.json to your OSF project (Files → OSF Storage → Upload). This records

exactly what was frozen and when — with a date that provably postdates your registration.

Claude Code shortcut: "run notebook 00 and tell me the checkpoint numbers" — it executes the

notebook headlessly and reports the counts. Optional; Run All in JupyterLab does the same.

# 3. PART THREE — Run the analysis pipeline (Analyst; ~2–3 h, mostly unattended)

Run these notebooks in order, each with Run → Run All Cells, reading the CHECKPOINT line at

the end of each before moving on. All except Stage 7 work entirely from the frozen snapshot (no live

API), so they are fully reproducible.

## 3.1 Stage 1 — Corpus (`01_corpus.ipynb`) — seconds

Builds the device table from the frozen 510(k) data. Checkpoint: unique device and summary counts,

matching SNAPSHOT.json.

## 3.2 Stage 2 — Download PDFs (`02_download_pdfs.ipynb`) — **1–3 hours**

Downloads each device's summary PDF from FDA. This is the long step. It saves a manifest and

resumes if interrupted — if it stops, just Run All again and it continues. Leave it running.

Checkpoint: ~92% of PDFs retrieved (older filings were never scanned — a known gap).

Claude Code shortcut: this is the best candidate for Claude Code — "run notebook 02 to completion,

resuming if it stops." It will babysit the long download. Manual alternative: just leave the notebook

running in JupyterLab.

## 3.3 Stage 3 — Extract edges (`03_extract_edges.ipynb`) — ~10 min

Reads each PDF's text and applies the deterministic edge rule (defined in prereg §5). Also draws the

fresh 60-device validation sample (see Part Four). Checkpoints: edge count, confidence-tier split,

and the coverage diagnostic (% cue / resolvable / name-only / out-of-scope).

## 3.4 Stage 4 — Recalls (`04_recalls.ipynb`) — seconds

Expands the recalls' structured k_numbers field to device-level links. Checkpoint: link count and

recalled-corpus-device count.

## 3.5 Stage 5 — Classify (`05_classify.ipynb`) — seconds

Attaches recall severity (Class I/II/III) from the enforcement data. Checkpoint: recalled-device count

and worst-class distribution.

## 3.6 Stage 6 — Graph and analysis (`06_graph_and_analysis.ipynb`) — ~1 min

The analytical heart. Builds the directed graph, confirms it's acyclic, and computes all primary

outcomes (prereg §6) — persistent recalled predicates, post-recall citations, downstream devices,

first-cited-after-recall, persistence gap, sensitivity subsets. **It writes data/expected_values.json

— the authoritative results.* Checkpoint: prints every headline number. These are the study's

findings — the first time they exist.*

## 3.7 Stage 7 — MAUDE clinical anchor (`07_maude.ipynb`) — ~5 min

Compares adverse-event burden of recalled predicates vs. a matched sample (prereg §8). Uses the live

MAUDE endpoint (event counts grow, so this is reported "as of" the run date). Checkpoint: family

totals, match rates, and the Mann-Whitney p-value.

## 3.8 Stage 8 — Verify your own run (`08_verify.ipynb`) — seconds

Rebuilds the graph from the edge list and re-checks every number against expected_values.json, in two

tiers (exact for deterministic results, ±2% for live-refetch counts). Checkpoint: a clean pass.

Record the outcome against the plan. Open PREREGISTRATION.docx §7. For each hypothesis H1–H5,

write in RUN_LOG.md whether the computed numbers met the pre-registered criterion — **including any

that did not.** Reporting non-confirmations is part of the honesty contract.

# 4. PART FOUR — Hand-validate the edges (Analyst; ~1–2 h)

The precision of the edge-mining is confirmed by a human, not assumed.

Open data/validation_sample.csv — 60 randomly chosen devices and the predicate K-numbers the

pipeline found for each.

For each row, open that device's cached text in data/text/<K-number>.txt (or the PDF in

data/summaries/).

Read the predicate section. Confirm each listed K-number is a genuine predicate/reference citation

(not an incidental mention, not a standards reference, not the device citing itself).

Tally: how many of the listed edges are correct (true positives) vs. wrong (false positives).

Precision = correct ÷ total listed. Record it with its Wilson 95% CI (prereg §8) in RUN_LOG.md.

This is deliberately manual — a person reading source documents is the validation. Budget an hour or

two; it is the most important quality check in the study.

# 5. PART FIVE — Publish the code on GitHub (Analyst, then Verifier)

## 5.1 Create the repository (Analyst)

github.com → ＋ → New repository.

Name: orthopedic-510k-predicate-graph  · Public · add README, .gitignore: Python,

License: MIT.

Create repository.

## 5.2 Push the project (Analyst)

From your project folder in a terminal:

cd ~/predicate-study
git init
git add notebooks/ requirements.txt README.md PREREGISTRATION.md PROJECT_RUN_MANUAL.md RUN_MANUAL.md .gitignore
git commit -m "Add analysis notebooks, preregistration, and manuals"
git branch -M main
git remote add origin https://github.com/<your-username>/orthopedic-510k-predicate-graph.git
git push -u origin main

Do NOT commit the large snapshot/*.json.gz files or the downloaded PDFs — the .gitignore

already excludes them. Those big files live on OSF (Part Six), not GitHub.

Claude Code shortcut: "initialise a git repo here, exclude the data folders, and push to my new

GitHub repo <URL>." It runs the git commands for you.

## 5.3 Link GitHub to OSF (Analyst)

In your OSF project → Add-ons → enable GitHub → authorize → select the repo. The OSF project now

shows the code, and the eventual DOI covers both.

## 5.4 Independent verification (Verifier — the OTHER person)

Fork the repo on GitHub (or git clone it) onto your own computer.

pip install -r requirements.txt.

Download the frozen snapshot files from the OSF project into a local snapshot/ folder.

In JupyterLab, run `08_verify.ipynb` first (fast check against the analyst's

expected_values.json), then optionally run the full pipeline (Stages 1, 3–6) to rebuild the

derived files yourself. Deterministic numbers must match exactly; a live re-fetch of counts may

drift up slightly and is checked within ±2%.

Do a hand spot-check: pick 2–3 devices, open their PDFs on accessdata.fda.gov, and confirm the

edges in predicate_edges.csv match what the documents say.

Open a pull request titled Independent verification — <name>, <date>, whose description is your

validation record: analyst's value vs. your recomputed value, PASS/FAIL for each headline number,

plus your spot-check results.

The Analyst reviews and merges the PR. That merge is the permanent public record that someone who

did not build the study reproduced it.

# 6. PART SIX — Deposit and mint a DOI on OSF (Analyst)

Once the run is verified:

In the OSF project, upload the full bundle: the frozen snapshot/ files (including the large

.json.gz), the derived data/ outputs, the final manuscript, and this manual.

Link the GitHub repo (if not already, §5.3).

Create a DOI: OSF project → Settings (or the Make DOI button) → Create DOI. This

gives the whole project a citable identifier.

In the manuscript, cite both the preregistration URL (from Part One) and the OSF project DOI, and

report any deviations from the plan in the DEVIATIONS.md log (prereg §11).

# The whole workflow on one line

**Register on OSF → freeze snapshot (Stage 0) → run Stages 1–8 → hand-validate edges → push to GitHub →

partner verifies via pull request → deposit on OSF + mint DOI.**

# Where Claude Code genuinely helps (all optional)

Babysitting the long PDF download (Stage 2) and resuming it.

Running a notebook headlessly and reporting its checkpoint numbers.

Driving the git commands for the initial push.

It cannot create your OSF/GitHub accounts, submit your registration, or merge your PR — those need

your identity and judgment.

# Troubleshooting

A notebook can't find a file → an earlier stage hasn't been run, or you're not launching

JupyterLab from the project folder. Run stages in order, from ~/predicate-study.

Stage 2 stops partway → just Run All again; it resumes from the manifest.

openFDA returns an error mid-fetch → wait a minute and re-run the cell; the API rate-limits

occasionally. All fetch stages are safe to re-run.

Verifier's counts are a few higher than the analyst's → expected if they re-fetched live from FDA

instead of using the frozen snapshot. The ±2% tier handles this. Deterministic numbers should still

match exactly.

Numbers don't match the earlier 9-code pilot → they shouldn't. This is the larger 154-code corpus;

different numbers are the intended result.